## Sheet1
Tasks | Start Date | Duration | End Date | Resource | Assignment
Mobilization(Getting NDA) | 2015-01-14 | 8 | 2015-01-22
Identifying the best suited algorithm | 2015-01-22 | 14 | 2015-02-05
Building the database | 2015-02-05 | 7 | 2015-02-12
Implementing the algorithm (Java) | 2015-02-05 | 21 | 2015-02-26
Algorithm Testing | 2015-02-26 | 5 | 2015-03-03
Mid-term presentation | 2015-03-02 | 1 | 2015-03-02
Spring Break | 2015-03-06 | 10 | 2015-03-16
Algorithm Enhancement | 2015-03-16 | 10 | 2015-03-26
Building the web interface(Backend, Frontend) | 2015-03-10 | 21 | 2015-03-31
Connecting the back end algorithm with interface. | 2015-03-31 | 7 | 2015-04-07
Testing | 2015-04-07 | 15 | 2015-04-22
Final Poster Day | TBD | 1 | TBD
Final Presentation | 2015-05-01 | 1 | 2015-05-01
* Final Poster Day and Final Presentation Day have not been finalized.
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]